## Reduced Operation
ASC Temporary Reduced Operations Checklist
Instructions
1. Review the list of action items below and customize (delete items that don't apply and insert new items) as necessary.
2. Assign responsible party(ies) to each activity, as well as a timeline for completion.
3. Update the work plan on a regular basis to note activity that has occurred in the "status" column and circulate to all members of the work team.
| Description of Work | Responsible Party(ies) | Date Completed | Status
ASC Operations
If you will maintain limited hours for urgent/emergent cases, provide guidance directives from CMS and other relevant professional organizations to the medical staff.
Notify landlord of reduction of ASC hours.
Determine appropriate staffing level to assure patient safety.
Communicate operational plan/reduction of hours to the medical staff with clarity including available hours, scheduling procedures, and the need for clearance by the Medical Director as appropriate. Compress the schedule as much as possible to conserve resources and optimize staffing.
Create a facilities checklist for any staff or physicians who may use the facility on an emergency patient basis. Include all facility open and closing duties (lights, alarm, computers, etc.). Include calling housekeeping if facility is used for emergency case. Powering off any items can help reduce utility bills while the ASC is vacant.
Review all service contracts. Determine if reduction or suspension is necessary and notify vendor to negotiate reduction/suspension as appropriate. i.e., laundry, fire extinguisher checks, housekeeping, etc.
Forward all email accounts to the Authorized Personnel or create an auto-reply away message with emergency contact info.
During reduction of hours, continue to utilize facility logs and compliance checklist on days of operation.
Create protocol for conducting and documenting post-op calls.
Review and revise HVA and ICRA to inlcude actions taken.
If a limited workforce continues to work in the facility, adhere strictly to CDC guidelines.
Notify State, CMS and acreditattion agencies of ASC reduction of hours.
Ensure that the ASC Emergency Preparedness Plan is up-to-date and that closure is appropriately communicated with staff.
Review and revise HVA and ICRA to reflect response.
Review your facility obligation as it relates to community wide disaster preparedness and communicate with your local/state CERT as appropriate to notify them of your limited operation.
Ensure PHI is secure for employees working remotely.
Financial Considerations
Check for emergency extensions, such as IRS: https://home.treasury.gov/news/press-releases/
Contact bank about potential loans for small businesses or emergency lines of credit.
Watch legislative updates that may offer new opportunities for funds/relief for business continuation.
Locate, reconcile, and secure petty cash funds. Determine how these funds will be used during this time.
Human Resources
Consult HR attorney to review options for managing reduction in workforce; layoffs, paid time off, furlough, etc. and best practices for management and communication.
Review all PTO balances for Employees. Manage PTO closely and communicate as appropriate to keep employees apprised.
Check with your benefit administrator or carrier to ascertain your options for maintenance of employee health benefits under these circumstances. Develop a plan and communicate appropriately to staff.
Make decisions regarding remote work, layoffs, paid time off (PTO), furlough, and communicate with clarity and compassion.
Adhere to legal advice regarding time frames for notice of closure and staff layoffs if necessary.
Prepare re-recruitment emails and job postings, and be ready to offer something great to new recruits at the other end of this crisis.
Communicate payroll changes/plans with payroll company if outsourced.
Prioritize weekly communications to minimize angst and keep people positive. The hope is to retain good employees and help others so they can return to work when the time comes.
If any employees are working from home, ensure they have access to clock in or develop system for team to track their hours. Consider creating new department codes to indicate that staff are working from remote locations.
Create checklist of terminated employees. Checklist should include the type of separation: termination, furlough, emergency FMLA, Layoff, available PTO, options for re-hire, re-instatement to position, other benefits Checklist should also include employees currently working, number of hours working.
If employees will be working from home, contact worker's compensation carrier to determine anf changes/pollicy updates are needed.
Following your workers' compensation carrier's guidance, communicate any updates in policy or instructions required for remote employees.
Billing Operations Considerations
Get remote access to all billing, scheduling, and patient notification platforms. Notify billing company of limited operations plan if outsourced.
Focus on AR collection, critical to cover payroll and liabilities. Consider managng AR remotely.
Have Authorized Individual run accounts receivable reports to create hard copy snapshot of collections. Include aging AR report, aging report by payer and patient, and any additional reports needed to work outstanding claims remotely. These reports may be back-up only but should be kept in a secure location and on file until billing operations return to the office.
Print out all insurance website usernames and passwords to research claims, eligibility, and prior authorizations to work AR.
Inventory Management
Work with vendors to set up delivery dates/times to ensure staff is onsite to accept deliveries.
Suspend or reduce any standing orders (packs, medical gas).
Print a list of open PO's/gather all open POs to ensure continuity of inventory management (all PO's get closed).
Secure all supplies, particularly PPE, disinfectant wipes, hand sanitizer, paper products, etc. to preclude pilfering.
Communication Plan
Commincate to your patients how your facility is maintaining a safe environment during your limited hours (ie, temperature screening upon arrival, limiting number of patients in facility, patients ride to wait in car, etc).
Create text groups for employees, medical staff and owner/partners. Send test texts to be sure all is working and so no one is searching for numbers later.
Post signage on entry doors for patients as to closure/limited service plan.
Update website with notice of reduced hours of operation.
Change away messages to include reduction of hours information.
Script key messaging for staff to communicate to patients on phone and in person.
Reach out to all scheduled patients to let them know their surgeon will contact them to reschedule when things return to normal.
Life Safety Requirements
Weekly
Emergency generator inspection: Verify enclosure is secure, area is clean and free of debris, and there are no conditions that can interfere with effective operation. This should be documented upon completion.
Monthly
Emergency Generator Testing: Conduct a 30-minute load test at 30% of the nameplate rating of the generator. This should be documented upon completion.
Emergency Egress Lighting: Perform and document a functional test of all battery-powered required for egress for a minimum of 30 seconds.
Perform or obtain testing report of monthly line isolation monitoring circuits.
Inspect all portable fire extinguishers per NFPA 10 standards
Fire sprinkler testing: Log completion of physical environment checklist for fire pump churn test, control valve inspection and pressure gauge inspection, as applicable.
Quarterly
Fire Alarm Testing: Test supervisory switches – low level and low water.
Fire Sprinkler Testing: Inspect fire department connections and fire hoses, as applicable
HVAC Inspection: Have HVAC vendor conduct inspection and service, per manufacturer recommendations.
Semi-Annually
Fire alarm systems: Inspect all tamper switches and document upon completion.
Other Considerations